Introduction to Scrum

---
Scrum in 100 words
Scrum is an agile method that allows us to focus on delivering the highest business value in the shortest time.
It allows us to rapidly and repeatedly inspect actual working software every two weeks to one month.
The business sets the priorities. Teams self-organize to determine the best way to deliver the highest priority features.
Every two weeks to a month anyone can see real working software and decide to release it as is or continue to enhance it for another sprint.

---
Scrum origins
Scrum origins
Jeff Sutherland
Initial scrums at Easel Corp in 1993
IDX and 500+ people doing Scrum
Ken Schwaber
ADM
Scrum presented at OOPSLA 96 with Sutherland
Author of three books on Scrum
Mike Beedle
Scrum patterns in PLOPD4
Ken Schwaber and Mike Cohn
Co-founded Scrum Alliance in 2002,
initially within the Agile Alliance

---
Scrum has been used by:
Scrum has been used by:
Microsoft
Yahoo
Google
Electronic Arts
Lockheed Martin
Philips
Siemens
Nokia
IBM
Capital One
BBC
Intuit
Nielsen Media
First American Real Estate
BMC Software
Ipswitch
John Deere
Lexis Nexis
Sabre
Salesforce.com
Time Warner
Turner Broadcasting
Oce

---
Scrum has been used for:
Scrum has been used for:
Commercial software
In-house development
Contract development
Fixed-price projects
Financial applications
ISO 9001-certified applications
Embedded systems
24x7 systems with 99.999% uptime requirements
the Joint Strike Fighter
Video game development
FDA-approved, life-critical systems
Satellite-control software
Websites
Handheld software
Mobile phones
Network switching applications
ISV applications
Some of the largest applications in use

---
Characteristics
Characteristics
Self-organizing teams
Product progresses in a series of fixed-length “sprints”
Requirements are captured as items in a “product backlog”
No specific engineering practices prescribed
Uses generative rules to create an agile environment for delivering projects

---
The Agile Manifesto–a statement of values
The Agile Manifesto
a statement of values
Source: www.agilemanifesto.org
Process and tools
Individuals and interactions
over
Following a plan
Responding to change
over
Comprehensive documentation
Working software
over
Contract negotiation
Customer collaboration
over

---
Project noise level
Project noise level
Far from
Agreement
Anarchy
Complex
Source: Strategic Management and Organizational Dynamics by Ralph Stacey in Agile Software Development with Scrum by Ken Schwaber and Mike Beedle.
Simple
Close to
Agreement
Technology
Complicated
Requirements
Close to
Certainty
Far from
Certainty

---
Scrum
Scrum
Product
backlog
Cancel
Gift wrap
Return
Sprint
2-4 weeks
Return
Sprint goal
Sprint backlog
Potentially shippable
product increment
Coupons
Gift wrap
Coupons
Cancel
24 hours

---
Putting it all together
Putting it all together
Image available at www.mountaingoatsoftware.com/scrum

---
Sprints
Sprints
Product is designed, coded, and tested during a series of sprints
Typical length 2–4 weeks; a calendar month at most
A constant duration leads to a better rhythm

---
Sequential vs. overlapping development
Sequential vs. overlapping development
Requirements
Design
Code
Test
Rather than doing all of one thing at a time...
...Scrum teams do a little of everything all the time
Source: “The New New Product Development Game” by Takeuchi and Nonaka. Harvard Business Review, January 1986.

---
No changes during a sprint
No changes during a sprint
Change
Plan sprint duration around how long you can commit to keeping change out of the sprint

---
Scrum framework
Scrum framework
Product owner
Scrum Master
Team
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts

---
Scrum framework
Artifacts
Product backlog
Sprint backlog
Burndown charts
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product owner
Scrum Master
Team
Roles

---
Product owner
Product owner
Define the features of the product
Decide on release date and content
Be responsible for the profitability of the product (ROI)
Prioritize features
Adjust features and priority every iteration, as needed
Accept or reject work results

---
The ScrumMaster
The Scrum Master
Represents management to the project
Responsible for enacting Scrum values and practices
Removes impediments
Ensure that the team is fully functional and productive
Enable close cooperation across all roles and functions
Shield the team from external interference

---
The team
The team
Typically 5-9 people
Cross-functional:
Programmers, testers, user experience designers, etc.
Members should be full-time
May be exceptions (e.g., database administrator)
Teams are self-organizing
Ideally, no titles but rarely a possibility
Membership should change only between sprints

---
Scrum framework
Product owner
ScrumMaster
Team
Roles
Product backlog
Sprint backlog
Burndown charts
Artifacts
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies

---
Sprint planning meeting
Team capacity
Product backlog
Business conditions
Current product
Techno-logy
Sprint prioritization
Analyze and evaluate product backlog
Select sprint goal
Sprint planning
Decide how to achieve sprint goal (design)
Create sprint backlog (tasks) from product backlog items (user stories / features)
Estimate sprint backlog in hours
Sprint
goal
Sprint
backlog

---
Sprint planning
Sprint planning
Team selects items from the product backlog they can commit to completing
Sprint backlog is created
Tasks are identified and each is estimated (1-16 hours)
Collaboratively, not done alone by the ScrumMaster
High-level design is considered
As a vacation planner, I want to see photos of the hotels.
Code the middle tier (8 hours)
Code the user interface (4)
Write test fixtures (4)
Code the foo class (6)
Update performance tests (4)

---
The daily scrum
The daily scrum
Parameters
Daily
15-minutes
Stand-up
Not for problem solving
Whole world is invited
Only team members, ScrumMaster, product owner, can talk
Helps avoid other unnecessary meetings

---
Everyone answers 3 questions
Everyone answers 3 questions
These are not status for the Scrum Master
They are commitments in front of peers
What did you do yesterday?
1
What will you do today?
2
Is anything in your way?
3

---
The sprint review
The sprint review
Team presents what it accomplished during the sprint
Typically a demo of new features or underlying architecture
Informal
2-hour prep time rule
No slides
Whole team participates
Invite everyone

---
Sprint retrospective
Sprint retrospective
Take a look at what is and is not working
Typically 15–30 minutes
Done after every sprint
Whole team participates
Scrum Master
Product owner
Team
Possibly customers and others

---
Start / Stop / Continue
Start / Stop / Continue
Whole team gathers and discusses what they’d like to:
Start doing
Stop doing
Continue doing
This is just one of many ways to do a sprint retrospective.

---
Scrum framework
Product owner
Scrum Master
Team
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts

---
Product backlog
Product backlog
The requirements
A list of all desired work on the project
Ideally expressed such that each item has value to the users or customers
Prioritized by the product owner
Re-prioritize at the start of each sprint
This is the product backlog

---
A sample product backlog
A sample product backlog
Backlog item
Estimate
Allow a guest to make a reservation
3
As a guest, I want to cancel a reservation.
5
As a guest, I want to change the dates of a reservation.
3
As a hotel employee, I can run RevPAR reports (revenue-per-available-room)
8
Improve exception handling
8
...
30
...
50

---
The sprint goal
The sprint goal
A short statement of what the work will be focused on during the sprint
Life Sciences
Support features necessary
for population genetics studies.
Database Application
Make the application run on SQL Server in addition to Oracle.
Financial services
Support more technical indicators than company ABC with real-time, streaming data.

---
Managing the sprint backlog
Managing the sprint backlog
Individuals sign up for work of their own choosing
Work is never assigned
Estimated work remaining is updated daily
Any team member can add, delete or change the sprint backlog
Work for the sprint emerges
If work is unclear, define a sprint backlog item with a larger amount of time and break it down later
Update work remaining as more becomes known

---
A sprint backlog
A sprint backlog
Tasks
Mon
Tues
Wed
Thur
Fri
Code the user interface
Code the middle tier
Test the middle tier
Write online help
Write the foo class
8
16
8
12
8
4
12
16
8
4
11
8
4
8
8
Add error logging
8
10
16
8
8

---
A sprint burndown chart
A sprint burndown chart
Hours

---
Tasks
Mon
Tues
Wed
Thur
Fri
Code the user interface
8
Code the middle tier
16
Test the middle tier
8
Write online help
12
50
40
30
20
10
0
Mon
Tue
Wed
Thu
Fri
Hours
4
12
16
7
11
8
10
16
8

---
Scalability
Scalability
Typical individual team is 7 ± 2 people
Scalability comes from teams of teams
Factors in scaling
Type of application
Team size
Team dispersion
Project duration
Scrum has been used on multiple 500+ person projects

---
Scaling through the Scrum of scrums
Scaling through the Scrum of scrums

---
Scrum of scrums of scrums
Scrum of scrums of scrums

---
Where to go next
Where to go next
www.mountaingoatsoftware.com/scrum
www.scrumalliance.org
www.controlchaos.com
scrumdevelopment@yahoogroups.com

---
A Scrum reading list
A Scrum reading list
Agile and Iterative Development: A Manager’s Guide by Craig Larman
Agile Estimating and Planning by Mike Cohn
Agile Project Management with Scrum by Ken Schwaber
Agile Retrospectives by Esther Derby and Diana Larsen
Agile Software Development Ecosystems by Jim Highsmith
Agile Software Development with Scrum by Ken Schwaber and Mike Beedle
Scrum and The Enterprise by Ken Schwaber
User Stories Applied for Agile Software Development by Mike Cohn
Lots of weekly articles at www.scrumalliance.org

---
Copyright notice
Copyright notice
You are free:
to Share―to copy, distribute and transmit the work
to Remix―to adapt the work
Under the following conditions
Attribution. You must attribute the work in the manner specified by the author or licensor (but not in any way that suggests that they endorse you or your use of the work).
For more information see http://creativecommons.org/licenses/by/3.0/

---
Contact information
Contact information
Presentation by: Mike Cohn
mike@mountaingoatsoftware.com
www.mountaingoatsoftware.com
(720) 890-6110